## Schedule of Works
| 15/1395 Alterations to Liskeard Public Hall |  |  | Dayworks |  |  | Rate
|  |  |  | Foreman |  |  | 0
|  |  |  | Tradesman |  |  | 0
| Valuation no.: | 0 |  | Groundworker |  |  | 0
| Valuation Date: |  |  | Unskilled |  |  | 0
| Valuation Issue Date: |  |  | Plant |  |  | Cost + %
|  |  |  | Materials |  |  | Cost + %
|  |  |  | Sub Contract |  |  | Cost + %
Revision B (22/05/2018) - revisions highlighted
(All figures are exclusive of VAT)
(Allow to make good for all works)
| Element | Element Total |  | Weeks | Progress | Updated This Valuation? | Valuation
1 | contractor overheads & profit | 0 |  |  | 0% |  | 0
2 | scaffolding | 0 |  |  | 0% |  | 0
3 | Main Entrance Corridor | 0 |  |  | 0% |  | 0
3.01 | Front door - redecorate | 0 |  |  | 0% |  | 0
3.02 | inner entrance doors - change for painted single solid 4 panel timber purpose made door 864x2083mm approx. of style to match existing outer door with 2no. Double glazed side lights, new frame/architrave/ironmongery | 0 |  |  | 0% |  | 0
3.03 | new acoustic suspended ceiling with recessed LED lights in 600x600mm ceiling grid from inner door to arch at bottom of stairs, allow to relocate M&E | 0 |  |  | 0% |  | 0
3.04 | alter drains | 0 |  |  | 0% |  | 0
3.05 | new anti-slip lino flooring, remove existing | 0 |  |  | 0% |  | 0
3.06 | demolitions | 0 |  |  | 0% |  | 0
3.07 | lift pit/slab | 0 |  |  | 0% |  | 0
3.08 | install lift by specialist | 0 |  |  | 0% |  | 0
3.09 | redecorate throughout | 0 |  |  | 0% |  | 0
3.1 | new door to rear corridor adjacent wc - replace with FD30s 16G 838x1981mm single ply painted door, alter opening to suit, with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
3.11 | new door to rear corridor - new 60min fire rated stud partition decorated | 0 |  |  | 0% |  | 0
3.12 | adjacent door in rear corridor - new ceiling surface mounted LED lights | 0 |  |  | 0% |  | 0
4 | Long Room
4.01 | new door to corridor - replace with FD30s 864x2083mm 16G single ply painted door with new ironmongery/lining/architrave & decorate, mains mag hold back | 0 |  |  | 0% |  | 0
4.01 | new plasterboard suspended ceiling with recessed 600x600mm LED lights, ceiling to slope up parallel to ramp at west end, between beams, redecorate beam encasements | 0 |  |  | 0% |  | 0
4.02 | redecorate throughout | 0 |  |  | 0% |  | 0
4.03 | new flotex floor finish, remove existing | 0 |  |  | 0% |  | 0
5 | Kitchen 1
5.01 | infill door to new caretaker's rest room & decorate | 0 |  |  | 0% |  | 0
5.02 | new lights in kitchen | 0 |  |  | 0% |  | 0
5.03 | remove dumb waiter & form timber stud cupboard with 762x1981mm ply painted door with ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
5.04 | infill ceiling/floor in dumb waiter shaft | 0 |  |  | 0% |  | 0
5.05 | redecorate throughout | 0 |  |  | 0% |  | 0
5.06 | new anti-slip lino flooring with coved skirtings, remove existing | 0 |  |  | 0% |  | 0
6 | Caretaker's Room
6.01 | new door to corridor - replace with FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
6.02 | new anti-slip lino flooring, remove existing | 0 |  |  | 0% |  | 0
7 | Facilities Office
7.01 | demolitions | 0 |  |  | 0% |  | 0
7.02 | move DB where partition being demolished | 0 |  |  | 0% |  | 0
7.03 | new door to corridor - replace with FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
7.04 | alter M&E, add new dado trunking to walls with 8np. Double sockets, 2no. BT point facess & 2no. data point faces in positions TBA | 0 |  |  | 0% |  | 0
7.05 | New 60min fire rated partitions to main entrance corridor | 0 |  |  | 0% |  | 0
7.06 | 600x1200mm FD60s roller shutter servery hatch (counter 760mm above FFL) | 0 |  |  | 0% |  | 0
7.07 | new anti-slip lino flooring, remove existing | 0 |  |  | 0% |  | 0
8 | WC & Baby Changing
8.01 | new door to corridor - replace with FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
8.02 | new baby changing table wall mounted | 0 |  |  | 0% |  | 0
9 | Mayor's Parlor
9.01 | new door to corridor - replace with FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave, alter 60min fire rated partition to suit & decorate | 0 |  |  | 0% |  | 0
10 | Stair
10.01 | remove stairlift | 0 |  |  | 0% |  | 0
10.02 | new anti-slip lino flooring with anti-slip contrasting mosings to treads/landing/half landing/raised boxing adjacent Quimperle south stair, remove existing | 0 |  |  | 0% |  | 0
10.03 | redecorate handrails & balusters | 0 |  |  | 0% |  | 0
11 | WC's at Stair Landing
11.01 | new 2no. doors to corridor - replace with FD30s 762x1981mm 16G single ply painted door with new ironmongery/lining/architrave, alter 60min fire rated partition to suit & decorate | 0 |  |  | 0% |  | 0
12 | Stairwell
12.01 | redecorate throughout | 0 |  |  | 0% |  | 0
12.02 | recessed | 0 |  |  | 0% |  | 0
12.03 | scrape/skim artex ceiling so smoothe | 0 |  |  | 0% |  | 0
12.04 | new 2no. doors to corridor - replace with FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
12.05 | remove 2no. Windows to west side at high level, made good openings, install 2no. frameless glass guarding to 1100mm above FFL in openings
13 | Quimperle Room
13.01 | replace 2no. lower level glass/frames to stirwell with 60min fire rated glass/painted frames | 0 |  |  | 0% |  | 0
13.02 | new door to corridor - replace with FD30s 762x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
14 | Council Chamber
14.01 | demolitions | 0 |  |  | 0% |  | 0
14.02 | trim back existing decorations & keep (wall paper, flooring etc), remove wall plaques & set aside then refix in positions TBA | 0 |  |  | 0% |  | 0
14.03 | new 60min fire rated partitions with flat ceiling over at 2.3m above FFL with deck over (as floor spec) | 0 |  |  | 0% |  | 0
14.04 | new door to stair - replace with FD30s 762x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate (alternate hanging) | 0 |  |  | 0% |  | 0
14.05 | new door to wc/lift lobby - FD60s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
14.06 | new lights to lift landing/lobby | 0 |  |  | 0% |  | 0
14.07 | decorate new work & make good existing decorations only, other existing finishes/decorations to remain | 0 |  |  | 0% |  | 0
14.08 | move existing radiator on north wall to east where new wc/lift lobby to be formed | 0 |  |  | 0% |  | 0
15 | Council Chamber Accessible WC
15.01 | new anti-slip lino with coved skirtings, extending through new lobby, remove existing | 0 |  |  | 0% |  | 0
15.02 | strip wall paper, skim walls, decorate throughout | 0 |  |  | 0% |  | 0
15.03 | new door to lobby - FD60s 864x2083mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
15.04 | demolitions | 0 |  |  | 0% |  | 0
15.05 | new 60min fire rated stud partitions | 0 |  |  | 0% |  | 0
15.06 | new doc-M pack including sanitaryware, grab rails, alarm, mirror etc | 0 |  |  | 0% |  | 0
15.07 | white ceramic tile splachback to basin 600x300mm | 0 |  |  | 0% |  | 0
15.08 | new hand drier | 0 |  |  | 0% |  | 0
15.09 | new sensor light to wc & wc lobby | 0 |  |  | 0% |  | 0
16 | Refreshment Room
16.01 | demolitions, including removal of canopy & bar/counter | 0 |  |  | 0% |  | 0
16.02 | redecorate throughout | 0 |  |  | 0% |  | 0
16.03 | new double doors to corridor/stairwell - FD60s 16G ply painted doors with ironmongery/lining/architrave & decorate, mag hold backs, o/a 1500x2100mm | 0 |  |  | 0% |  | 0
16.04 | new flotex floor finish, remove existing | 0 |  |  | 0% |  | 0
16.05 | remove WC & fan in ceiling | 0 |  |  | 0% |  | 0
16.06 | form new cupboard to match adjacent in lieu of wc | 0 |  |  | 0% |  | 0
16.07 | remove radiator on wc wall, new radiator to equivalent output on adjacent external wall (between east window & new cupboard) | 0 |  |  | 0% |  | 0
16.08 | strip wallpaper to west wall, skim, decorate | 0 |  |  | 0% |  | 0
16.09 | replace masonry pier with steel column as engineer's design, new floor boards to continue existing to suit | 0 |  |  | 0% |  | 0
16.1 | new suspended ceiling with recessed LED lights in 600x600mm ceiling grid run into sloping ceiling on south side | 0 |  |  | 0% |  | 0
16.11 | new door to west stairwell - FD30s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave, infill head with fire rated stud partition & decorate | 0 |  |  | 0% |  | 0
17 | Kitchen 2
17.01 | demolitions | 0 |  |  | 0% |  | 0
17.02 | infill 2no. Doors in 60min timber stud partitions (to Refreshment Room & west corridor) & decorate | 0 |  |  | 0% |  | 0
17.03 | new lights in kitchen, new corridor & cupboard | 0 |  |  | 0% |  | 0
17.04 | remove dumb waiter | 0 |  |  | 0% |  | 0
17.05 | infill ceiling/floor in dub waiter shaft | 0 |  |  | 0% |  | 0
17.06 | redecorate throughout | 0 |  |  | 0% |  | 0
17.07 | new anti-slip lino flooring with coved skirtings througout, with conrasting stair nosings, remove existing | 0 |  |  | 0% |  | 0
17.08 | doors to Refreshment Room - 2no. New pairs of doors as door/ironmongery schedule with new/altered openings & lintels to suit with new architraves & linings | 0 |  |  | 0% |  | 0
17.09 | new steps to corridor | 0 |  |  | 0% |  | 0
17.1 | new timber floor structure to corridor | 0 |  |  | 0% |  | 0
17.11 | dub out & render & decorate walls to corridor | 0 |  |  | 0% |  | 0
17.12 | new lintel(s) over new opening in wall to corridor | 0 |  |  | 0% |  | 0
17.13 | box in existing drains/pipes/gulley | 0 |  |  | 0% |  | 0
17.14 | remove existing ME vent pipe, stud frame, plasterboard face, dair board finish | 0 |  |  | 0% |  | 0
17.15 | alter M&E for kitchen installation by others | 0 |  |  | 0% |  | 0
17.16 | new PCC lintel(s) where wall removed due to ceiling level differences | 0 |  |  | 0% |  | 0
17.17 | new dairyboard to walls to kitchen / new corridor | 0 |  |  | 0% |  | 0
17.18 | form new stud/plasterboard cupboard around 3phase & DB with new MDF painted hinged access door to front approx. 800x800x300mm | 0 |  |  | 0% |  | 0
17.19 | boiler to remain in-situ | 0 |  |  | 0% |  | 0
17.2 | infill door to corridor to east | 0 |  |  | 0% |  | 0
17.21 | form new stud/plasterboard boxing around flues with new MDF painted hinged access door(s) to front, relocate heating controls | 0 |  |  | 0% |  | 0
17.22 | new 2no. doors to Refreshment Room - FD60s 864x2083mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
17.23 | 900x900mm FD60s roller shutter servery hatch (counter 900mm above FFL) | 0 |  |  | 0% |  | 0
17.24 | new door to Stage Area - FD60s 838x1981mm 16G single ply painted door with new ironmongery/lining/architrave & decorate | 0 |  |  | 0% |  | 0
17.25 | new door to Stage Area - infill above new door head with 60min fire rated stud partition, drop cill/threshold to suit new door position | 0 |  |  | 0% |  | 0
18 | Main Hall
18.01 | demolitions | 0 |  |  | 0% |  | 0
18.02 | new 2no. double doors to stairwell - replace with FD30s 16G (1no. pair 838x1981mm, 1no. pair 686x1981mm) ply painted doors with new ironmongery/lining/architrave, alter partition to suit & decorate, mag hold backs | 0 |  |  | 0% |  | 0
18.03 | new 1no. double doors to Kitchen 2 corridor - FD60s 16G (o/a 1500x2100mm) ply painted doors with new ironmongery/lining/architrave, alter partition to suit, new PCC lintel(s) over & decorate | 0 |  |  | 0% |  | 0
18.04 | new 1no. double doors to Kitchen 2 corridor - alter partition to suit, new PCC lintel(s) over | 0 |  |  | 0% |  | 0
18.05 | new 60min fire rated partition to pair doors to kitchen 2 corridor | 0 |  |  | 0% |  | 0
18.06 | stage - new 60min fire rated stud partition at stage | 0 |  |  | 0% |  | 0
18.07 | stage - new floor infill | 0 |  |  | 0% |  | 0
18.08 | stage - new 60min. Fire rated ceiling to underside lighting gantry | 0 |  |  | 0% |  | 0
18.09 | stage - new stair | 0 |  |  | 0% |  | 0
18.1 | stage - alter ladder to lighting rig & asociated edge guarding to same | 0 |  |  | 0% |  | 0
18.11 | stage - new ceiling lighting to corridor | 0 |  |  | 0% |  | 0
19 | Landing & Corridor to Lift / Liskeard Room
19.01 | remove glazedscreen/doors to stairwell & make good | 0 |  |  | 0% |  | 0
19.02 | new flotex floor finish, remove existing | 0 |  |  | 0% |  | 0
19.03 | redecroate throughout | 0 |  |  | 0% |  | 0
19.04 | scrape/skim artex ceiling so smoothe | 0 |  |  | 0% |  | 0
19.05 | new stair nosings | 0 |  |  | 0% |  | 0
19.06 | new 60min fire rated stud partition to full height | 0 |  |  | 0% |  | 0
19.07 | strip wall paper east wall, skim walls between existing windows to stairwell | 0 |  |  | 0% |  | 0
19.08 | remove stair to Council Chamber | 0 |  |  | 0% |  | 0
19.09 | move DB adjacent door to Council Chamber above stair to same to adjacent wall | 0 |  |  | 0% |  | 0
19.1 | demolitions | 0 |  |  | 0% |  | 0
19.11 | install lift by specialist | 0 |  |  | 0% |  | 0
19.12 | redecorate throughout | 0 |  |  | 0% |  | 0
19.13 | extend raised floor to new Council Chamber lobby | 0 |  |  | 0% |  | 0
19.14 | M&E alterations | 0 |  |  | 0% |  | 0
20 | General
20.01 | make good insection holes in boxings/ceilings | 0 |  |  | 0% |  | 0
20.02 | make good existing where altered by works | 0 |  |  | 0% |  | 0
21 | Provisional Sums
21.01 | Contingencies | 10000 |  |  | 0% |  | 0
21.02 | Platform lift supply by specialist | 20000 |  |  | 0% |  | 0
21.03 | Supply of light fittings | 5000 |  |  | 0% |  | 0
21.1 | Supply of wall/floor finishes & adhesives (£50/sq.m) |  |  |  | 0% |  | 0
AI 1 |  | NOTES | OMIT | ADD | Progress |  | Valuation
1.1 |  |  | 0 | 0 | 0% |  | 0
1.2 |  |  | 0 | 0 | 0% |  | 0
Daywork Sheets |  | NOTES |  | ADD | Progress |  | Valuation
1 |  |  |  | 0 | 0% |  | 0
2 |  |  |  | 0 | 0% |  | 0
|  | Contract Sum | OMIT | ADD | Variation |  | Valuation
| Totals: |  | 0 | 0 | 0 |  | 0
(All figures are exclusive of VAT)